## Sheet2 (hidden)
Review concern | Yes
Count of Status | Column Labels
Row Labels | Open | Inprogress | Hold | Closed | Not Valid | WOC | (blank) | Grand Total
Sales |  |  | 1 | 8 | 4 |  |  | 13
RM |  |  |  | 8 |  |  |  | 8
Packing |  |  |  | 6 |  |  |  | 6
Production | 2 | 3 | 1 |  |  |  |  | 6
Warehouse |  |  |  | 1 |  | 1 |  | 2
Logistics |  | 1 |  |  |  | 1 |  | 2
Grand Total | 2 | 4 | 2 | 23 | 4 | 2 |  | 37

## Review abstract
Module | Review planned date | Review status | Remarks
Enquiry | 2024-10-18 | Signedoff
Sales | 2024-10-18 | Waiting on BMR team | Review Issues/Suggestions cleared and BMR team need to validate
Rawmaterial | 2024-10-19 | Waiting on BMR team | Review Issues/Suggestions cleared and BMR team need to validate
Packing | 2024-10-21 | Waiting on BMR team | Review Issues/Suggestions cleared and BMR team need to validate
Warehouse | 2024-10-21 | Signedoff | Data migration pending for 3 weeks as data is not yet shared hemce considered as auto signedoff
Production | 2024-10-22 | Inprogress | CR's raised while review/ Financial efforts need to be approved If CR's are not required then module can be considered as signed off as no issues raised today in flow
Logistics | 2024-10-23 | Inprogress | Preshipment print cncerns will be cleared by24/10/2024 Postshipment print concerns need to be shared
Finance | 2024-10-23 | Open

## Issue details
Sno | Module | screen | Review concern | Task | type | Status | Remarks | BMR
1 | Sales | customs invoice | Yes | Mam/sir can't able to open po -148052 Customs invoice in document register | Bug | Closed |  | confirmed
2 | Sales | customs invoice / All Buyer | Yes | vesel num and name should not come in customs invoice ..in any pre shipment | CR | Closed |  | confirmed
3 | Sales | customs invoice / Canada Buyer | Yes | hsn code for canada | Bug | Closed | .. | confirmed
4 | Sales | customs invoice / UAE Buyer | Yes | fob value wrong | Bug | Closed |  | confirmed
5 | Sales | customs invoice / Japan Buyer | Yes | fob value wrong ...... | Bug | Closed |  | confirmed
6 | Sales | customs invoice / USA Buyer | Yes | hsn code missing | Bug | Closed | .. | confirmed
7 | Sales | customs invoice / USA Buyer | Yes | amount calci wrong | Bug | Closed | Issue cleared need to correct pending data | reopen(pP846609,y0888)
8 | Sales | customs invoice / USA Buyer | Yes | taxable value calcis wrong .... | Bug | Closed | Issue cleared need to correct pending data | reopen(pP846609,y0888)
9 | RM | Indent | Yes | Grder -1 is not mandatory for dealer in indent form | CR | Closed |  | confirmed
10 | RM | Report | Yes | 2.Date filter need to be added in count wise qty summary report | CR | Closed |  | confirmed
11 | RM | GRN print | Yes | Pls correct the F/Y 24-25 instead of 25-26. And Qty digits should not rounded off. Ex. 4366.600 Kgs | Bug | Closed |  | confirmed
12 | RM | Invoice | Yes | Invoice defect material quantity and rate captured error in GRN no. 1621 | Bug | Closed |  | confirmed
13 | RM | GRN | Yes | Pls delete the GRN No. A20/R-1630 | Bug | Closed |  | confirmed
14 | RM | GRN | Yes | need to show reweighment quantities in GRN print if reweighment is done else GRNs | service request | Closed |  | confirmed
15 | RM | Invoice print | Yes | need to show reweighment quantities in invoice print for reweghment GRNs | Bug | Closed |  | confirmed
16 | Packing | Report | Yes | aging filter in dead stock report duplicate values showing in dead stock report (3-6 ,6-12months/ 1 yr & above | CR | Closed
17 | Packing | Report | Yes | need to change column labels (sandya aqua unit names are hardcoded as column header) in packing stock report | CR | Closed
18 | Packing | Material issues | Yes | need to add issued to in direct store issues (Material Issues) screen | CR | Closed
19 | Packing | Report | Yes | need to show issued to in store consumption report | CR | Closed
20 | Packing | Report | Yes | Brand is showing for general items in stock report | CR | Closed
21 | Packing | Report | Yes | PO and GRN print corrections | Bug | Closed
22 | Warehouse | Stockin | Yes | need to remove compliments in Trasaction type dropdown in stock in form | Bug | Closed
23 | RM | Report | Yes | 4. Need excel dowloads which are missed for few reports | CR | Closed |  | confirmed
24 | Warehouse | Migration | Yes | Data migration | CR | WOC | Task in open since 3 week as data required to migrate not provided
25 | Logistics | Prints | Yes | Post shipment prints | N/A | WOC | Prints shall be given once pre shipments are done
26 | Production | value addition | Yes | stock after valuaddtion can be given as compliment need option to save this | CR | Hold | Rare scenario not of priority shall be added post signoff
27 | Production | Report | Yes | Need to check Grade analysis report (Values not showing) | Bug | Inprogress | PCD: 24/10/2024
28 | Production | Report | Yes | Need to check Grade analysis report (Values not showing) | Bug | Inprogress | PCD: 24/10/2024
29 | Production | Reports | Yes | option to transfer multiple batch numbers at one time in stock transfer | CR | Inprogress | PCD: 24/10/2024
30 | Logistics | Prints | Yes | Preshimpent prints | Bugs/CR | Inprogress | PCD: 24/10/2024 (customs completed / packing list inprogress)
31 | Sales | customs invoice / China Buyer | Yes | remove amount in isd afdditional destination ..until cnf | Bug | Closed |  | CNF ZHANJIANG PORT, CHINA ----YS02-Y01-020
32 | Sales | customs invoice / Canada Buyer | Yes | price usd getting wrong in canada | Bug | Not Valid | it is convereted to kg from lb | confirmed
33 | Sales | customs invoice / China Buyer | Yes | product description need to check once for china | process concern | Not Valid | working as expected, added extra space in description | confirmed
34 | Sales | customs invoice / UAE Buyer | Yes | size getting wrong in uae ... | Bug | closed | according to data it was rendered | closed
35 | Sales | customs invoice / Japan Buyer | Yes | supply meant wrong for japan(small letters) | Bug | closed | working as expected | closed
36 | Production |  | Yes | Need to enter direct entry of grading for HL material where HL done at ouside (here third party bill generation is not responsiblilty of BMR) |  |  | CR takes time Efforts need to be approved in mail sent
37 | Production | Report | Yes | Lot wise tracking report | CR | Open | CR takes time Efforts need to be approved in mail sent
38 | Production | Report | Yes | Worker wise bill generation | CR | Open | CR takes time Efforts need to be approved in mail sent
39 | RM | Invoice print | No | Batch wise qty should be shown in invoice print | Bug | closed
40 | Sales | customs invoice / Canada Buyer | No | for highliner...ship to should come instead of buyer for canada | CR | Closed |  | New
41 | Sales | customs invoice / Japan Buyer | No | place of supply ...CFR add in | CR | cancelled
42 | Sales | customs invoice / Japan Buyer | No | shipment terms also should get CFR | CR | Closed |  | New
43 | Sales | customs invoice / USA Buyer | No | usfda regn num compulsory for usa .......... At packed and processed | CR | Closed |  | New
44 | RM | GRN print | No | deffects should show in grn print | CR | Open |  | New
45 | RM | Invoice print | No | Defects need to be added in invoice print | CR | Open |  | New
44 | RM | Reweighment | No | seal no should capture | CR | Open |  | New
| RM | GRN print | No | vehicle number not showing in some prints | Bug | Open |  | New
| RM | rm receiving report | No | qty and count should get from reweightment and rate from invoice | bug | open |  | New

## Sheet4
submodule | screen | Task | type | Assignee | Status
Document register | packing list / canada | full address required for consignee address for | process concern | sunanda | Not Valid | confirmed
Document register | packing list / canada | please insert shipto address in buyer box | Bug | sunanda | Not Valid | reopen | only for HIGH LINER
Document register | packing list / canada | full description is missing | process concern | sunanda | Not Valid | confirmed
Document register | packing list / canada | item code required | Bug | sunanda | Not Valid | confirmed
Document register | packing list / canada | Quantity should be in KGs | Bug | sunanda | Closed | confirmed
Document register | packing list / canada | HSN required | Bug | sunanda | Closed | confirmed
Document register | packing list / canada | total should be render in the place of TEMP and TEMP should be under the remarks box | Bug | Naveen | Inprogress | Open
Document register | packing list / canada | Packed and processed by address is wrong | Bug | vineela | Closed | reopen | approval number is wrong
Document register | packing list / canada | please remove empty row above the decleration | Bug | vineela | Closed | confirmed
Document register | packing list / canada | need to change decleration | CR | vineela | Closed | confirmed
Document register | packing list / china | full address required for consignee address for | process concern | sunanda | Not Valid | confirmed
Document register | packing list / china | net weight is wrong | Bug | sunanda | Closed | confirmed
Document register | packing list / china | total should be render in the place of TEMP and TEMP should be under the remarks box | Bug | Naveen | Inprogress | Open
Document register | packing list / china | Packed and processed by address is wrong | Bug | vineela | Closed | reopen | approval number is wrong
Document register | packing list / china | please remove empty row above the decleration | Bug | vineela | Closed | confirmed
Document register | packing list / china | need to change decleration | CR | vineela | Closed | confirmed
Document register | packing list / USA | notify party address is missing | Bug | sunanda | Not Valid | confirmed
Document register | packing list / USA | description of goods is mssing | Bug | sunanda | Not Valid | confirmed
Document register | packing list / USA | quantity is wrong need to show net weight | Bug | sunanda | Closed | confirmed
Document register | packing list / USA | total should be render in the place of TEMP and TEMP should be under the remarks box | Bug | Naveen | Open | Open
Document register | packing list / USA | Packed and processed by address is wrong | Bug | vineela | Closed | reopen | approval number is wrong
Document register | packing list / USA | please remove empty row above the decleration | Bug | vineela | Closed | confirmed
Document register | packing list / USA | need to change decleration | CR | vineela | Closed | confirmed
Document register | packing list / Tokyo | full address required for consignee address for | process concern | sunanda | Not Valid | confirmed
Document register | packing list / Tokyo | quantity is wrong need to show net weight | Bug | sunanda | Closed | confirmed
Document register | packing list / Tokyo | Packed and processed by address is wrong | Bug | vineela | Closed | reopen | approval number is wrong
Document register | packing list / Tokyo | please remove empty row above the decleration | Bug | vineela | Closed | confirmed
Document register | packing list / Tokyo | need to change decleration | CR | vineela | Ready For Testing | confirmed
Document register | packing list / UAE | full address required for consignee address for | process concern | sunanda | Not Valid | confirmed
Document register | packing list / UAE | remove empty space in description of goods | Bug | vineela | Closed | confirmed
Document register | packing list / UAE | quantity is wrong need to show net weight | Bug | sunanda | Closed | confirmed
Document register | packing list / UAE | remove repeated HSN codes | Bug | sunanda | Closed | confirmed
Document register | packing list / UAE | total should be render in the place of TEMP and TEMP should be under the remarks box | Bug | Naveen | Open
Document register | packing list / UAE | Packed and processed by address is wrong | Bug | vineela | ReOpen | reopen | approval number is wrong
Document register | packing list / UAE | please remove empty row above the decleration | Bug | vineela | Closed | confirmed

## Abstract
Modules | Open | Inprogress | Hold | Closed | Not Valid | WOC | Grand Total
Sales |  |  | 1 | 8 | 4 |  | 13 | Review concerns cleared and BMR team need to validate
RM |  |  |  | 8 |  |  | 8 | Review concerns cleared and BMR team need to validate
Packing |  |  |  | 6 |  |  | 6 | Review concerns cleared and BMR team need to validate
Production | 2 | 3 | 1 |  |  |  | 6 | Bugs will be cleared by tomorrow/ New Reports requested, efforts need to be approved
Warehouse |  |  |  | 1 |  | 1 | 2 | Data migration pending
Logistics |  | 1 |  |  |  | 1 | 2 | Preshipment invoices will be completed by 23/10/2024 Postshipment prints need to be shared
Grand Total | 2 | 4 | 2 | 23 | 4 | 2 | 37

## Pending ACtion items
Module | Task | Who | PCD | Status | Remarks
Warehouse | Data need to be given for migration | Vasudha | 2024-10-06 | Cancelled | BMR team not provided data
Production | Financial efforts need to be given for the CR' raised | Praveen | 2024-10-24 | Open | Efforts shared over mail
Logistics | Post shipment prints concerns need to be shared | Siva krishna | 2024-10-25 | Open | Will be shared once pre shipment issues are cleared
Logistics | Preshipment concerns need to be completed | Uma | 2024-10-24 | Inprogress | Will be completed by 25/10/2024
Sales | Completed concerns need to be validated | Siva krishna | 2024-10-25 | Open | Will be completed by 25/10/2024 morning session
Packing | Completed concerns need to be validated | Giri | 2024-10-25 | Open | Will be completed by 25/10/2024 morning session
RM | Completed concerns need to be validated | Suresh | 2024-10-25 | Open | Will be completed by 25/10/2024 morning session